## Cover Page
Big Data Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  |  | 2024-08-13
Project Team Name |  |  | Nhóm 1 – BD02
Project Topic |  |  | Phân tích dự đoán giá nhà đất
Task |  |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5 |  |  |  |  | W6 |  |  |  |  | W7 |  |  |  |  | W8 |  |  |  |  | W9 |  |  |  |  | W10 |  |  |  |  | W11
[9 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74 | D75
 | time axis 2024-06-01 to 2024-08-14
1. Thu thập dữ liệu |  |  |  | 2024-01-06 | 24/6/2024 |  |  | Done | bar: 2024-06-01 to 2024-06-24
| 1.1. Thu thập dữ liệu |  |  | 2024-01-06 | 2024-10-06 |  |  | Done | bar: 2024-06-01 to 2024-06-10
|  | 1.1.1. Xác định các nguồn dữ liệu liên quan |  | 2024-01-06 | 2024-03-06 | Ngô Văn Lâu | Danh sách các nguồn dữ liệu đã xác định. | Done | bar: 2024-06-01 to 2024-06-03
|  | 1.1.2. Tải xuống hoặc thu thập các bộ dữ liệu. |  | 2024-04-06 | 2024-10-06 | La Hồng Lộc | Bộ dữ liệu đầy đủ từ các nguồn đã thu thập. | Done | bar: 2024-06-04 to 2024-06-10
| 1.2. Chuẩn bị dữ liệu |  |  | 2024-11-06 | 24/6/2024 |  |  | Done | bar: 2024-06-11 to 2024-06-24
|  | 1.2.1. Load dữ liệu |  | 2024-11-06 | 13/6/2024 | La Hồng Lộc | Dữ liệu đã được load thành công vào hệ thống. | Done | bar: 2024-06-11 to 2024-06-13
|  | 1.2.2. Quan sát và kiểm tra cấu trúc của bộ dữ liệu |  | 14/6/2024 | 24/6/2024 | Ngân Hoàng Huy | Báo cáo về cấu trúc dữ liệu và các vấn đề tiềm ẩn. | Done | bar: 2024-06-14 to 2024-06-24
2. Tiền xử lý dữ liệu |  |  |  | 18/6/2024 | 2024-07-07 |  |  | Done | bar: 2024-06-18 to 2024-07-07
| 2.1. Làm sạch dữ liệu |  |  | 18/6/2024 | 25/6/2024 |  |  | Done | bar: 2024-06-18 to 2024-06-25
|  | 2.1.1. Xử lý các giá trị bị thiếu (missing values) |  | 18/6/2024 | 20/6/2024 | Trần Tuấn Kiệt | Bộ dữ liệu đã được làm sạch, không còn giá trị thiếu. | Done | bar: 2024-06-18 to 2024-06-20
|  | 2.1.2. Chuyển đổi kiểu dữ liệu hợp lý hơn cho các thuộc tính |  | 21/6/2024 | 23/6/2024 | Lê Đông Anh Kiệt | Dữ liệu đã được điều chỉnh và nhất quán. | Done | bar: 2024-06-21 to 2024-06-23
|  | 2.1.3. Phát hiện và xử lý các giá trị ngoại lệ (outliers) |  | 24/6/2024 | 25/6/2024 | Lê Đông Anh Kiệt | Dữ liệu không còn giá trị ngoại lệ hoặc đã được điều chỉnh hợp lý. | Done | bar: 2024-06-24 to 2024-06-25
| 2.2. Trích lọc đặc trưng |  |  | 26/6/2024 | 2024-03-07 |  |  | Done | bar: 2024-06-26 to 2024-07-03
|  | 2.2.1. Tạo các đặc trưng mới |  | 26/6/2024 | 27/6/2024 | Lê Đông Anh Kiệt | Bộ dữ liệu với các đặc trưng mới. | Done | bar: 2024-06-26 to 2024-06-27
|  | 2.2.2. Mã hóa các biến phân loại |  | 28/6/2024 | 30/6/2024 | Lê Đông Anh Kiệt | Bộ dữ liệu với các biến phân loại đã được mã hóa. | Done | bar: 2024-06-28 to 2024-06-30
|  | 2.2.3. Chuẩn hóa, điều chỉnh các đặc trưng |  | 2024-01-07 | 2024-03-07 | Lê Đông Anh Kiệt | Bộ dữ liệu đã được chuẩn hóa và điều chỉnh. | Done | bar: 2024-07-01 to 2024-07-03
| 2.3. Phân chia dữ liệu |  |  | 2024-04-07 | 2024-07-07 |  |  | Done | bar: 2024-07-04 to 2024-07-07
|  | 2.3.1. Chia dữ liệu thành tập huấn luyện và tập kiểm tra |  | 2024-04-07 | 2024-07-07 | Ngô Văn Lâu | Bộ dữ liệu được phân chia thành công thành các tập huấn luyện và kiểm tra. | Done | bar: 2024-07-04 to 2024-07-07
3. Phát triển mô hình |  |  |  | 2024-08-07 | 14/8/2024 |  |  | Done | bar: 2024-07-08 to 2024-08-14
| 3.1. Lựa chọn mô hình |  |  | 2024-08-07 | 2024-10-07 |  |  | Done | bar: 2024-07-08 to 2024-07-10
|  | 3.1.1. Đánh giá các mô hình khác nhau |  | 2024-08-07 | 2024-10-07 | Ngân Hoàng Huy | Báo cáo đánh giá mô hình. | Done | bar: 2024-07-08 to 2024-07-10
| 3.2. Huấn luyện mô hình |  |  | 2024-11-07 | 24/7/2024 |  |  | Done | bar: 2024-07-11 to 2024-07-24
|  | 3.2.1. Huấn luyện mô hình bằng tập huấn luyện |  | 2024-11-07 | 14/7/2024 | Lê Đông Anh Kiệt | Mô hình đã được huấn luyện. | Done | bar: 2024-07-11 to 2024-07-14
|  | 3.2.2. Điều chỉnh tham số (cross-validation) |  | 15/7/2024 | 19/7/2024 | La Hồng Lộc | Mô hình với tham số được điều chỉnh. | Done | bar: 2024-07-15 to 2024-07-19
|  | 3.2.3. Giám sát quá trình huấn luyện |  | 20/7/2024 | 24/7/2024 | Nguyễn Đặng Phú Mẫn | Báo cáo quá trình huấn luyện. | Done | bar: 2024-07-20 to 2024-07-24
| 3.3. Đánh giá mô hình |  |  | 25/7/2024 | 2024-08-08 |  |  | Done | bar: 2024-07-25 to 2024-08-08
|  | 3.3.1. Đánh giá mô hình dựa trên tập kiểm tra |  | 25/7/2024 | 31/7/2024 | Lê Đông Anh Kiệt | Báo cáo đánh giá mô hình trên tập kiểm tra. | Done | bar: 2024-07-25 to 2024-07-31
|  | 3.3.2. So sánh hiệu suất các mô hình bằng |  | 2024-01-08 | 2024-08-08 | Trần Tuấn Kiệt | Bảng so sánh hiệu suất của các mô hình. | Done | bar: 2024-08-01 to 2024-08-08
| 3.4. Lựa chọn mô hình |  |  | 2024-09-08 | 14/8/2024 |  |  | Done | bar: 2024-08-09 to 2024-08-14
|  | 3.4.1. Chọn mô hình có hiệu suất tốt nhất |  | 2024-09-08 | 14/8/2024 | Lê Đông Anh Kiệt | Mô hình cuối cùng đã được lựa chọn và sẵn sàng triển khai | Done | bar: 2024-08-09 to 2024-08-14